## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	(Fill your team name here)
PROJECT NAME	(Fill your project name here)
PROJECT MENTOR	(Put your Mentor name here)
TEAM MEMBERS	Team Mamber Name 1
	Team Member Name 2
	Team Member Name 3
	Team Member Name 4
	Team Member Name 5

## Team_Status
TEAM NAME	(Fill your team name here)
PROJECT NAME	(Fill your project name here)
PROJECT MENTOR	(Put your Mentor name here)

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 5 (August 31- sept 6)
Learn Eclipse	Preparation	Elliot	4		Planned	Using IDEs can make our job easier
Role preferences	Coordination	Matt	0.5	0.3	Done		0.2	66.6666666667
Web framework setup	Preparation	John	1	1.5	Ongoing		-0.5	33.3333333333
Discuss bug report software	Preparation	Seth	1.5	0	Delayed	This is critical to project success	1.5
Develop questions for requirements elicitation	Documentation	Sean	5		Planned	Make sure scoping questions are included
Get account and configure website	Preparation	Elliot	1.5	1	Done		0.5	50
Research existing technology	Preparation	Matt	2	1.5	Ongoing		0.5	33.3333333333
Project synopsis writeup	Documentation	Elliot	2		Planned
Identify role owners	Preparation	Matt	1	0.6	Done	Multiple roles are OK - think about role & reponsibility distribution	0.4	66.6666666667
Team Meeting	Coordination	John	1	2	Done		-1	50
Status tracker	Documentation	Seth	1		Planned
Week 6 (sept 7- sept 13)

Week 8 (sept 14 - sept 20)

Week 9

Week 10

Week 11

Week 12

Week 13

Week 14

Week 15

Week 16

Week 17

## Individual_Status
TEAM NAME	SSAD 46
PROJECT NAME	MSME CLOUD
PROJECT MENTOR	MR. VISHAL KADGE

Actvities	SAUMYA SHRIVASTAVA		MADHUR AGGARWAL		REVANTH THOTA		RAMA ROHIT		VAMSI		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
WEEK 5 (AUGUST 31- SEPT 6)
INSTALL MAGENTO	2 WEEKS	17 DAYS	2 WEEKS	17 DAYS	2 WEEKS	17 DAYS	2 WEEKS	17 DAYS	2 WEEKS	17 DAYS	#VALUE!	#VALUE!
ROLE PREFERENCES						0	0
WEB FRAMEWORK SETUP						0	0
DISCUSS BUG REPORT SOFTWARE						0	0
DEVELOP QUESTIONS FOR REQUIREMENTS ELICITATION						0	0
GET ACCOUNT AND CONFIGURE WEBSITE						0	0
RESEARCH EXISTING TECHNOLOGY						0	0
PROJECT SYNOPSIS WRITEUP						0	0
IDENTIFY ROLE OWNERS						0	0
TEAM MEETING						0	0
STATUS TRACKER						0	0
WEEK 6 (SEPT 7- SEPT 13)
INSTALL MAGENTO(WEB FRAMEWORK SETUP)	1 WEEK	10 DAYS	1 WEEK	10 DAYS	1 WEEK	10 DAYS	1 WEEK	10 DAYS	1 WEEK	10 DAYS	#VALUE!	#VALUE!
TEAM MEETINGS	MEETINGS WERE HELD ON ALTERNATE DAYS TO DISCUSS THE ISSUES WE WERE HAVING IN SETTING UP THE WEB FRAMEWORK.
0						0	0
0						0	0
0						0	0
0						0	0
WEEK 8 (SEPT 14 - SEPT 20)
LEARNING MAGENTO(RESEARCH EXISTING TECHNOLOGY)	2 WEEKS	2 WEEKS	2 WEEKS	2 WEEKS	2 WEEKS	2 WEEKS	2 WEEKS	2 WEEKS	#VALUE!	#VALUE!
MAGENTO THEME CHANGE	4 DAYS	3 DAYS	4 DAYS	3 DAYS	4 DAYS	3 DAYS	4 DAYS	3 DAYS	4 DAYS	3 DAYS	#VALUE!	#VALUE!
MAGENTO CODING	2 WEEKS	2 WEEKS	2 WEEKS	2 WEEKS	2 WEEKS	2 WEEKS	2 WEEKS	2 WEEKS	#VALUE!	#VALUE!
TEAM MEETINGS	MEETINGS WERE HELD ON ALTERNATE DAYS TO DISCUSS ON HOW AND WHERE TO LEARN THE TECHNOLOGY FROM.
WEEK 9						0	0
0						0	0
0						0	0
WEEK 10						0	0
0						0	0
0						0	0
0						0	0
WEEK 11						0	0
0						0	0
0						0	0
0						0	0
WEEK 12						0	0
0						0	0
0						0	0
0						0	0
0						0	0
WEEK 13						0	0
0						0	0
0						0	0
0						0	0
0						0	0
WEEK 14						0	0
0						0	0
0						0	0
0						0	0
0						0	0
WEEK 15						0	0
0						0	0
0						0	0
0						0	0
WEEK 16						0	0
0						0	0
0						0	0
0						0	0
0						0	0
WEEK 17						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0